## Feature Status
PREMIUM JOURNAL — FEATURE STATUS
Feature | Status | Session | V1 | Notes | Last Updated
INFRASTRUCTURE
Storage abstraction layer (db/index.ts) | BUILT | A2 | IN | Single interface, Phase B swap-ready | 2026-03-02
localStorage CRUD — all data types | BUILT | A2 | IN | entries, habits, eras, threads, questions, longform | 2026-03-02
Full export/import JSON | BUILT | A2 | IN | db.backup.exportAll() / importAll() | 2026-03-02
Tag normalisation | BUILT | A6a | IN | Lowercase, trim, deduplicate on every save | 2026-03-02
NAVIGATION
Left sidebar — 3 groups | BUILT | A2 | IN | Today / Understand / Explore / Settings | 2026-03-02
Sidebar collapse to icon-only | BUILT | A2 | IN |  | 2026-03-02
Mobile slide-in drawer | BUILT | A2 | IN |  | 2026-03-02
Default landing: Timeline | BUILT | A3b | IN | Changed from Write in A3b | 2026-03-02
WRITE
Quick / Guided / Deep mode switcher | BUILT | A4 | IN |  | 2026-03-02
Guided mode — 5 writing fields | BUILT | A4 | IN | whatHappened, feelings, whatMatters, insight, freeWrite | 2026-03-02
Deep Write — word count | BUILT | A4e | IN | Fades in once writing starts, no target | 2026-03-02
Deep Write — typewriter scroll | BUILT | A4e | IN | Active line stays centred | 2026-03-02
Deep Write — amber caret | BUILT | A4e | IN | caretColor: #f59e0b | 2026-03-02
Mood selector — compact emoji row | BUILT | A6b-polish | IN | Label animates in on select only | 2026-03-02
Energy selector — bars only | BUILT | A6b-polish | IN | No number labels. Single row with mood. | 2026-03-02
Closing moment after save | BUILT | A4 | IN | Full-screen overlay, new entries only | 2026-03-02
Unsaved changes guard | BUILT | A4 | IN | window.confirm on Cancel if dirty | 2026-03-02
Year-ago memory surface | BUILT | A4 | IN | ±3 day window | 2026-03-02
Continuity prompt (yesterday) | BUILT | A4 | IN | Suppressed for reflections | 2026-03-02
TagManager — inline autocomplete | BUILT | A6a | IN | Enter/comma/Backspace | 2026-03-02
Intention field | BUILT | A4c | IN | Reflections only | 2026-03-02
One-word closing field | BUILT | A5a | IN | Reflections only, single word enforced | 2026-03-02
Era selector in Write | PLANNED | A7a | TBD | Decision needed: manual/auto/hybrid | 2026-03-02
TIMELINE
Year heatmap — 12 months × daily dots | BUILT | A3b | IN | Mood-coloured | 2026-03-02
Drill-down year→month→week→day | BUILT | A3b | IN | Breadcrumb nav | 2026-03-02
Month / Week / Day views | BUILT | A3b | IN |  | 2026-03-02
Reflection panels | BUILT | A4c | IN | Full content, intention at top | 2026-03-02
Welcome card (first-run) | BUILT | A4d | IN | Animates out after first entry | 2026-03-02
Tag filter — activeTagFilter | BUILT | A6b | IN | All drill levels fade unmatched | 2026-03-02
DayView tag pills clickable | BUILT | A6b | IN | Sets filter + navigates to year | 2026-03-02
Era overlay on heatmap | PLANNED | A7b | TBD | Background band behind dots | 2026-03-02
REFLECTIONS
Weekly / Monthly / Yearly entries | BUILT | A4b | IN | Synthetic date keys | 2026-03-02
Reflection panels (Month/Week/Year) | BUILT | A4c | IN |  | 2026-03-02
HABITS
HabitBuilder view | BUILT - NEEDS POLISH | A1 | IN | Original Figma export | 2026-03-02
21-day gentle start visual | BUILT | A2 | IN | 3×7 grid, celebration state | 2026-03-02
No streaks philosophy | BUILT | A2 | IN | Locked product decision | 2026-03-02
ERAS
Era CRUD (basic) | BUILT - NEEDS POLISH | A1 | IN | Unstyled, eras.ts not shimmed | 2026-03-02
eras.ts shim → db.eras | PLANNED | A7a | IN | 15 min, mechanical | 2026-03-02
ErasManager redesign | PLANNED | A7a | IN | Warm minimal design language | 2026-03-02
Era colour palette (6 warm) | PLANNED | A7a | IN | Must not clash with mood system | 2026-03-02
Era surfaces on Timeline | PLANNED | A7b | TBD |  | 2026-03-02
SEARCH
Full-text keyword search | DEFERRED | A6c | TBD | Build at 30+ entries | 2026-03-02
Filtered browse (mood+date+tag) | PLANNED | A6c phase 2 | TBD |  | 2026-03-02
PRIVACY
Full export/import all data | BUILT | A2 | IN | db.backup covers all types | 2026-03-02
Zero telemetry | BUILT | A1 | IN | Permanent product decision | 2026-03-02
ONBOARDING
Welcome card (first-run empty state) | BUILT | A4d | IN |  | 2026-03-02
Guided first entry | PLANNED | TBD | TBD | Not yet scheduled | 2026-03-02
PHASE B
Electron wrapper | PLANNED | B1 | POST-V1 |  | 2026-03-02
electron-store file storage | PLANNED | B1 | POST-V1 | Replaces localStorage | 2026-03-02
GitHub Actions CI builds | PLANNED | B2 | POST-V1 | Linux/Windows/Mac | 2026-03-02
NEVER
AI reading entries | NEVER | — | NEVER | Violates privacy principle | 2026-03-02
Streak counters | NEVER | — | NEVER | Gamification — manager not witness | 2026-03-02
Social sharing | NEVER | — | NEVER | Private by design always | 2026-03-02

## Docs Status
PREMIUM JOURNAL — DOCUMENT STATUS
Document | Status | Location | Last Updated | Trigger | What's Missing / Stale
BA-Document.docx | NEEDS UPDATE | docs/BA-Document.docx | A2 (2026-02-28) | A2 | Sections 3,4,5,6,9,11 empty. Stale at A2. Needs update to A6b-polish.
PRD.md | NOT STARTED | docs/PRD.md | — | — | Full document needed. Write after V1-Scope.md locked.
V1-Scope.md | NOT STARTED | docs/V1-Scope.md | — | — | Full document needed. First priority in Doc Sprint 1.
FRD.md | NOT STARTED | docs/FRD.md | — | — | Full document needed. All behavioural rules.
SRS.md | NOT STARTED | docs/SRS.md | — | — | Full document needed. Data models, storage contracts.
User-Journey.md | NOT STARTED | docs/User-Journey.md | — | — | Extract from BUILDLOG Day 1/7/30/365/10,000 framework.
Flow-Diagrams.md | NOT STARTED | docs/Flow-Diagrams.md | — | — | Write, Save, Timeline, Tag filter flows as Mermaid.
AI-Process-Case-Study.md | NOT STARTED | docs/AI-Process-Case-Study.md | — | — | Portfolio differentiator. Human-led AI development story.
Early-Adopter-Brief.md | DEFERRED | docs/Early-Adopter-Brief.md | — | — | Build when 30+ real entries exist.
DOCS-STATUS.md | COMPLETE | docs/DOCS-STATUS.md | 2026-03-02 | Doc Sprint planning
FEATURE-STATUS.md | COMPLETE | docs/FEATURE-STATUS.md | 2026-03-02 | Doc Sprint planning
DECISIONS-LOG.md | COMPLETE | docs/DECISIONS-LOG.md | 2026-03-02 | Doc Sprint planning
BUGS-AND-DEBT.md | COMPLETE | docs/BUGS-AND-DEBT.md | 2026-03-02 | Doc Sprint planning
INDEX.md | COMPLETE | docs/INDEX.md | 2026-03-02 | Doc Sprint planning
PROJECT-TRACKER.xlsx | COMPLETE | docs/PROJECT-TRACKER.xlsx | 2026-03-02 | Doc Sprint planning

## Decisions Log
PREMIUM JOURNAL — DECISIONS LOG
Decision | Choice | Date | Status | Options Considered | Why | Trigger to Revisit
Product Philosophy
Core philosophy — The Witness | The Witness | Pre-A1 | LOCKED | Manager vs Witness | Manager is common. Witness is rare, honest, privacy-first. | Never
Streak counters | Never build | Pre-A1 | LOCKED | Streaks / no streaks | Gamification. Violates Witness. | Never
AI reading entries | Never build | Pre-A1 | LOCKED | AI analysis / none | Privacy non-negotiable. | Never
Telemetry | Zero, none, never | Pre-A1 | LOCKED | Analytics / none | No data leaves device ever. | Never
Architecture
Phase 1 storage | localStorage via db interface | A2 | LOCKED | localStorage/IndexedDB/SQLite | Simple, offline. Abstraction = Phase B is one-file swap. | Phase B start
Export format | Human-readable JSON | Pre-A1 | LOCKED | JSON/CSV/proprietary | Open format. User owns it. Permanence. | Never
Navigation
Default landing view | Timeline | A3b | LOCKED | Write / Timeline | Timeline shows emotional landscape. More meaningful. | User feedback
Write
Mood position | Top, compact row | A6b-polish | LOCKED | Top large / bottom / top compact | Bottom risks mood never set. Compact = capture without dominating. | User feedback
Prompt chips | Decided against | A5a | LOCKED | Chips / no chips | Clutter before writing starts. Manager move. | Never
Tags
Tag normalisation | Lowercase, trim, deduplicate | A6a | LOCKED | Normalise / don't | Prevents 'Work' and 'work' being different tags. | Never
Tag filter entry point | DayView only | A6b | LOCKED | Search/tag cloud/DayView | Discovery-led. Natural moment of curiosity. | User feedback
Search
Search timing | Deferred to 30+ entries | A6c brainstorm | REVISIT | Build now / defer | Build without knowing what you search = wrong feature. | 30+ entries
Eras
Era deletion | Un-tags entries, never deletes | Pre-A7a | LOCKED | Delete entries / un-tag | Entries are permanent record. Eras are organisational. | Never
Era colour palette | TBD — 6 warm colours | A7a brainstorm | REVISIT | Various | Must not clash with mood system on heatmap. | A7a build
Process
Brainstorm-first rule | Brainstorm before every build | 2026-03-02 | LOCKED | Build first / brainstorm first | Design decisions mid-build cost more than pre-build decisions. | Never

## Bugs & Debt
PREMIUM JOURNAL — BUGS & TECHNICAL DEBT
# | Severity | Issue | Component | Discovered | Fix Plan / Status
C1 | CRITICAL | localStorage 5-10MB limit. Silent failure at scale. | db/index.ts | A2 | Phase B solves. Phase A: add quota warning in PrivacySettings.
M1 | MAJOR | Deleting era does not un-tag entries. Orphaned eraId. | ErasManager.tsx | A7a brainstorm | Fix in A7a — loop entries on delete.
M2 | MAJOR | PrivacySettings export partial — missing post-A2 data types. | PrivacySettings.tsx | A2 | Update to use db.backup.exportAll(). Schedule polish session.
M3 | MAJOR | WelcomeMessage.tsx not reviewed — may have stale copy. | WelcomeMessage.tsx | A4d | Review in A9a or polish pass.
m1 | MINOR | ReflectionModeSelector.tsx may still exist as dead code. | ReflectionModeSelector.tsx | A4 | Delete file, confirm no imports.
m2 | MINOR | Year-ago ±3 day window may surface wrong-context entry. | JournalEntry.tsx | A4 | Revisit if user feedback identifies false positives.
m3 | MINOR | ErasManager has 7 colours incl. red — clashes with mood system. | ErasManager.tsx | A7a brainstorm | Replace palette in A7a.
m4 | MINOR | eras.ts getActive() only returns first ongoing era. | eras.ts | A7a brainstorm | Fix in A7a with overlap logic.
m5 | MINOR | Continuity prompt may display awkwardly if entry has quotes. | JournalEntry.tsx | A4 | Sanitise preview string.
co1 | COSMETIC | Multiple original components unstyled — ErasManager, Threads, Anchors etc. | Multiple | A1 | Each has dedicated redesign session (A7a, A8a, A9a, A10a).
co2 | COSMETIC | ErasManager info box uses old bg-slate-50 pattern. | ErasManager.tsx | A7a brainstorm | Remove or absorb into empty state in A7a.
D1 | DEBT | erasStorage still uses direct localStorage, not db.eras. | ErasManager.tsx / eras.ts | A7a brainstorm | Fix in A7a shim.
D2 | DEBT | Several utils may have unshimmed localStorage calls. | utils/ | A2 | Audit before Phase B.
D3 | DEBT | buildEntryMap() may lag at 1000+ entries. | TimelineView.tsx | A3b | useMemo wraps it. Monitor. Fix if perceptible.
D4 | DEBT | No React error boundary. Runtime error = blank white screen. | Global | A1 | Add error boundary. Schedule polish session.
D5 | DEBT | Two localStorage keys called directly in TimelineView, bypassing db. | TimelineView.tsx | A4d | Add to db.prefs or db.ui in Phase B prep.
F1 | FIXED | isSameDay unused import in JournalEntry.tsx | JournalEntry.tsx | A6a | Removed in A6a.
F2 | FIXED | Curly apostrophes in single-quoted strings | Multiple | A4b | Fixed in A4b.
F3 | FIXED | Blank screen when editing reflections from Timeline | App.tsx | A4c-fix | Fixed in A4c-fix.
F4 | FIXED | node_modules committed to GitHub | Repo | A1 | Fixed in A1.

## Session Roadmap
PREMIUM JOURNAL — SESSION ROADMAP
Session | Goal | Status | Files Changed | Depends On | Notes
PHASE A — WEB
A1 | Get It Running | BUILT | — | — | GitHub repo, all 14 views working
A2 | Storage Abstraction + Habits + Sidebar | BUILT | db/index.ts, storage.ts, App.tsx | A1
A3 | Mood & Energy Visual Upgrade | BUILT | JournalEntry.tsx | A2
A3b | Timeline / Heatmap Emotional Landscape | BUILT | TimelineView.tsx, App.tsx | A3
A4 | Write Section Redesign | BUILT | JournalEntry.tsx | A3b
A4b | Reflection Types via Timeline | BUILT | TimelineView.tsx, JournalEntry.tsx, App.tsx | A4
A4c | Reflection Panels + Intentions Loop | BUILT | TimelineView.tsx, JournalEntry.tsx, types.ts | A4b
A4d | First-Run Empty State + Below Heatmap | BUILT | TimelineView.tsx, JournalEntry.tsx, App.tsx | A4c
A4e | Deep Write Enhancements | BUILT | JournalEntry.tsx | A4
A5a | Write + Form Polish | BUILT | JournalEntry.tsx, types.ts | A4
A5b | Timeline + Global Polish | BUILT | TimelineView.tsx, fonts.css, theme.css | A5a
A6a | Tag Infrastructure | BUILT | db/index.ts, TagManager.tsx, JournalEntry.tsx | A5
A6b | Tag Navigation | BUILT | TimelineView.tsx | A6a
A6b-polish | Mood & Energy Compact Redesign | BUILT | JournalEntry.tsx | A6b
A6c | Search | DEFERRED | SearchView.tsx, App.tsx | A6a | Build at 30+ entries
A7a ← NEXT | Era Management | PLANNED | ErasManager.tsx, eras.ts, JournalEntry.tsx | A6a | Brainstorm done. 5 decisions pending.
A7b | Era Surfaces on Timeline | PLANNED | TimelineView.tsx, ErasManager.tsx | A6b + A7a
A8a | Inner Compass: Values | PLANNED | InnerCompass.tsx, App.tsx | A5
A8b | Inner Compass: Questions | PLANNED | InnerCompass.tsx, JournalEntry.tsx | A8a
A8c | Inner Compass: Lifecycle | PLANNED | InnerCompass.tsx, JournalEntry.tsx | A8b
A9a | Insights Audit + Witness Redesign | PLANNED | Insights.tsx, MoodChart.tsx | A5
A9b | Connected Insights | PLANNED | Insights.tsx, insights.ts | A6+A7+A8+A9a | POST-V1 candidate
A10a | Threads: Reading Experience | PLANNED | MemoryThreads.tsx | A5
A10b | Threads: Intelligent Building | PLANNED | MemoryThreads.tsx | A10a
A11a | Connecting the Dots: Passive | PLANNED | TimelineView.tsx, insights.ts | A9+A10
A11b | Connecting the Dots: Active | PLANNED | Multiple | A11a
DOC SPRINTS
Doc Sprint 1 | Foundation Docs | PLANNED | docs/ folder | A7a brainstorm done | SWOT, gap, V1 scope, user journey, trackers
Doc Sprint 2 | Formal Documents | PLANNED | docs/ folder | Doc Sprint 1 | PRD, FRD, SRS, flows, case study
PHASE B — ELECTRON
B1 | Electron Wrapper | PLANNED | electron/main.js, electron/preload.js | Phase A complete
B2 | GitHub Actions CI | PLANNED | .github/workflows/build.yml | B1
B3 | Polish & Final Testing | PLANNED | Multiple | B2